## Sheet1
Master Thesis Plan
WOY | Month | To do | Task | Meeting with supervisors | Status
Week 26 | July | Clean Data | Revision of S1 process and begin with the R script to ML (Adapt Eagle Lab) | Yes | Done
Week 27 | Juni | Clean Data | Analysis of fertilizer data and read of State of the Arte in Chile (Introduction) and more about Table grape phenology. | No | Done
Week 28 | July | Analysis of data | Multicollinearity test (Sensibility) | No | Done
Week 29 | July | Machine Learning process | Revision of result using the data | No | Almost
Week 30 | July | Revision with Supervisors | Revision of result with a presentation of (possible final results) | Yes
Week 31 | August | Focus in writing the thesis | Weekly thesis writing progress sent and / or discussed with supervisors (Dr. Sarah/ Dr. Thorsten). | No/Probably
Week 32 | August | Focus in writing the thesis | Weekly thesis writing progress sent and / or discussed with supervisors (Dr. Sarah/ Dr. Thorsten). | No/Probably
Week 33 | August | Focus in writing the thesis | Weekly thesis writing progress sent and / or discussed with supervisors (Dr. Sarah/ Dr. Thorsten). | No/Probably
Week 34 | August | Focus in writing the thesis | Weekly thesis writing progress sent and / or discussed with supervisors (Dr. Sarah/ Dr. Thorsten). | No/Probably
Week 35 | August | Focus in writing the thesis | Weekly thesis writing progress sent and / or discussed with supervisors (Dr. Sarah/ Dr. Thorsten). | No/Probably
Week 36 | September | Focus in writing the thesis | Meeting to analyze writing and finalize thesis process. | Yes
Week 37 | September | Final review with supervisors (Dr. Sarah) | Preparation of presentation and request for defense date | No/Probably
Week 38 | September | Ppt presentation | Preparation of presentation and request for defense date | Yes
Week 39 | September | Ppt presentation | Preparation of presentation and request for defense date | No/Probably
Week 40 | October
Week 41 | October
Week 42 | October
Week 43 | October
Note on D4: Meeting with Tobias Ullmann, He gaves me the script tp work with sentinel-1 and GEE direct
Note on D13: Time to read and prepare all/ discuss with friends